## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Login | Login account | Lectures, Students | Allows registered users to enter account name, password, remember password, link to Registration page | Đức Trung | Done | iter1 | none
2 | Register | Allow user create a new account | Lectures | Allows lectures to create a new account including email, username and password | Tùng | Done | iter1 | none
3 | Forgot password | Set new password | Lectures, Students | Allows users to change their password via previously registered email | Linh | Done | iter1 | none
4 | Change password in the first time login | Set new password | Students | Allows users to change password via email in case that account logs in for the first time | Trung | Done | iter1 | none
5 | Enter Capcha | Email verify | Lectures, Students | Verify the email exists and it is yours | Tùng | Done | iter1 | none
6 | View class | Classes manage | Lectures | Lecture can see all classes they teach | Bình | Done | iter1 | none
7 | Import file excel | Classes manage | Lectures | Lecture can import list students from excel file to system | Trung | Done | iter1 | none
8 | Show profile information | Account manage | Lectures, Students | User can see all information of your account | Minh | Done | iter1 | none
9 | Show project infomation | Project manage | Lectures, Students | Lectures can see all project of student they teach and Students can see all their project | Minh | Done | iter1 | none
10 | Show milestones of project | Milestone manage | Lectures, Students | Lecture can see all milestones of project of students and Students can manage milestone | Tùng | To Do | iter2 | none
11 | Add new milestones | Milestone manage | Students | Students can add new milestones | Linh | To Do | iter2 | none
12 | Remember account | Account manage | Lectures, Students | System can remember account of user | Linh | To Do | iter2 | none
13 | Update milestones | Milestone manage | Students | Students can update new milestones | Minh | To Do | iter2 | none
14 | Delete milestones | Milestone manage | Students | Students can delete new milestones | Bình | To Do | iter2 | none
15 | Add new task | Task manage | Students (TL) | TL student can add new task | Tùng | To Do | iter2 | none
16 | Update process task | Task manage | Students (TL) | TL student can update task | Trung | To Do | iter2 | none
17 | Delete task | Task manage | Students (TL) | TL student can delete task | Minh | To Do | iter2 | none
18 | Comment task | Task manage | Lectures, Students | Lectures and Students can comment in the task | Bình | Doing | iter2 | none
19 | View task | Task manage | Lectures, Students | Lectures and Students can see task in milestone | Linh | Doing | iter2 | none
20 | Filter task | Task manage | Lectures, Students | Lectures and Students can filter task in milestone | Linh | Doing | iter2 | none
21 | Report task | Daily report | Students | Students can report everyday | Tùng | Doing | iter2 | none
22 | Push code | Task manage | Students | Stuents can push code into system | Trung | Doing | iter2 | none
23 | View comment | Conversation | Lectures, Students | Lectures and Students can see all comment of task | Minh | Doing | iter2 | none
24 | Update comment | Conversation | Lectures, Students | Lectures and Students can see update comment of task | Tùng | Doing | iter2 | none
25 | Update daily report | Conversation | Students | Students can update daily report | Linh | Doing | iter2 | none
26 | Grade project | Grade project | Lectures | Lectures can grade project | Bình | Doing | iter2 | none
27 | View all issue | Task manage | Lectures, Students | Lectures and Students can see all issue of task | Bình | Doing | iter2 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none
[6 empty] | Doing | iter1 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Login | Login account | allows registered users to enter account name, password, remember password, link to Registration page, | Đức Trung | Done | II.3 | III.5
2 | Register | Register account from lecture | Allows only lecture to enter account name, email, password, confirm password, full name, and Register button. | Đức Minh | Done | II.1 | III.4
3 | Forgot password | Set new password | Allows users to enter account name, email, password, password confirmation, full name. | Quang Bình | Done | II.2 | III.5
4 | View Classes | Show all classes | Show all classes created by lecture or classes that student join by link | Tùng | Done

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4